## Sheet1
RISK ID | RISK DESCRIPTION | CATERGORY | LIKELIHOOD | IMPACT | RISKSCORE | LEVEL | MITIGATION | CONTINGENCY | OWNER | STATUS
R01 | Stakeholder does not approve the proposed solution or design | Stakeholder | 3 | 3 | 9 | High | Involves stakeholder in reviews, get feedback early and often, document all decisions. | Refine design based on feedback, escalate to lecturer if needed | Stakeholder Liaison | Closed
R02 | Stakeholder becomes unavailable or unresponsive | Stakeholder | 3 | 3 | 9 | High | Establish clear communication channels, schedule meetings in advance, have backup contact person. | Use documented findings to proceed, note limitations in final report | Stakeholder Liaison | Monitoring
R03 | Safety concerns during stakeholder visits (theft, dogs) | Operational | 1 | 2 | 2 | Low | Travel in groups, visit during safe hours, phone for meetings if possible | Switch to virtual meetings, reschedule if unsafe | Stakeholder Liaison | Closed
R04 | Learners or unauthorised user access teacher-delivered materials | Security | 1 | 3 | 3 | Low | Implement role based access control, must use Supabase RLS policies, secure authentication | Revoke access and investigate breach, notify stakeholders | Backend Lead | In Progress
R05 | Scope creep- stakeholder request for additional features | Scope | 3 | 3 | 9 | High | Define scope clearly in SRS, use "Must Have, Could Have, Should Have" prioritization. Document new request as Future Enhancements. | Re-evaluate priorities, cut Should-have features | Business Analyst | Monitoring
R06 | Team falls behind schedule | Schedule | 3 | 2 | 6 | Medium | Use Microsoft Project to track progress, ad buffer time, hold regular stand-up meetings. | Cut non-essential features, redistribute tasks | Project manager | In Progress
R07 | Integration issues between Flutter, ASP.NET, and Supabase | Technical | 2 | 3 | 6 | Medium | Test integration early, use official documentation, build incrementally. | Allocate extra time for integration testing, use alternative methods | Backend Lead | In Progress
R08 | Team members not attending meetings | Team | 2 | 2 | 4 | Medium | Set clear attendance expectation, schedule meetings at convenient times, record meeting minutes. | Follow up with absent members, escalate to lecturer if consistent | Project manager | Open
R09 | Regression Fault(new code breaks existing functionality | Technical | 2 | 2 | 4 | Medium | Use version control(Git), test before merging, use feature branches | Rollback to previous versions, fix bugs immediately | GitHub Manager | Open
R10 | Team members not completing assigned work | Team | 2 | 3 | 6 | Medium | Assign clear roles and deadlines, track the contribution on GitHub, hold regular check-in | Redistribute tasks, escalate to lecturer if possible | Project Manager | In Progress
R11 | Tasks taking longer than estimate | Schedule | 3 | 3 | 9 | High | Add buffer time to estimates, priorities Must Have requirements, track progress weekly | Reduce scope, cut Could Have or Should Have features | Project manager | Open
R12 | Using different or incomplete frameworks | Technical | 1 | 3 | 3 | Low | Agree on technology stack Phase 1, document decisions, ensure all members use same versions | Re-align development, allocate extra time for fixing compatibility | Technical Lead | Closed
| Highest Risk | Why is this important? | What must the group do now?
1 | R01- Stakeholder does not approve the proposed solution or design. | This is important because rejection of the proposed solution or design could require changes to the project and delay progress. | We can design based on feedback, escalate to lecture if needed
2 | R02- Stakeholder becomes unavailable or unresponsive | This is important because the team may not receive the feedback or decisions needed to continue with the project. | The group can use documented findings to proceed, note limitations in final report
3 | R05- Scope creep- The stakeholder adds additional features | It is important because additional features could increase the project scope and make it difficult to complete the project within the available time and resources | The group can re-evaluate priorities, cut "Should have" features